## Sheet1
Sprint | Duration | Sprint Goal | Major User Stories / Tasks | Deliverables | Status
Sprint 1 | 04/09/2025 - 19/09/2025 | Develop Customer Module | Implement Customer APIs (Create, Get, Update, Delete); Add validation for name, phone, email, Aadhar, PIN, DOB; Unit testing with JUnit and Mockito | Working Customer REST endpoints with full validation | Completed
Sprint 2 | 20/09/2025 - 03/09/2025 | Develop Account Module | Create Account APIs (Create, Fetch by Aadhar/Number, Update, Delete); Integrate AccountService & Repository; Validate IFSC, Account type, Bank name, Phone | Account module integrated with DB and tested | Completed
Sprint 3 | 04/10/2025 - 17/10/2025 | Develop Transaction Module and Testing | Build TransactionController (process, list, export CSV); Add amount, PIN, and account validations; Email notification logic for both parties; End-to-end testing for all modules; | Transaction workflows working and tested | Completed
Sprint 4 | 18/10/2025 - 31/10/2025 | Frontend & Documentation | Develop frontend for the application; Integration; Prepare Unit Test Plan, Defect Tracker, Agile summary | Fully tested project, documentation submitted | Completed